## Slide 1: 10th ACE Impact Regional Workshop ABIDJAN, COTE D’IVOIRE from 31st October to 3rd November 2023
Presentation by:
Prof. Ahmed Jinapor Abdulai
Director-General
Leading Tertiary Education to Greater Heights
Ghana ACE National Facilitation Unit Report

## Slide 2: Table of Content
Country Performance
  Countrywide Highlights
  Countrywide Disbursement
  DLR Achievement, by center
  Fund Utilization and Implementation Rate, by center
Challenges and Key Issues
2024 Next Steps

## Slide 3: General Overview
Ghana's Africa Higher Education Centers of Excellence (ACEs) has to total of 9 centers in 5 public universities. The centres are categorised into STEM, Health and Agriculture.
The nine (9) Ghana ACEs that participated are:
West Africa Center of Excellence for Cell Biology of Infectious Pathogens (WACCBIP), University of Ghana (UG);
West Africa Center of Excellence for Crop Improvement (WACCI), UG; the
Regional Water and Environmental Sanitation Center Kumasi (RWESCK), Kwame Nkrumah University of Science and Technology (KNUST); the
Africa Center of Excellence for Regional Transport Research Center (TRECK), KNUST; the
Africa Center of Excellence in Coastal Resilience (ACECOR), University of Cape Coast (UCC); the
West African Center for Water Irrigation and Sustainable Agriculture (WACWISA), University of Development Studies (UDS); the
Regional Center for Energy and Environmental Sustainability (RCEES), University of Energy and Natural Resources (UENR); the
West African Genetic Medicine Center (WAGMC), UG; and the
KNUST Engineering Education Project (KEEP).

## Slide 4: General Overview
Ghana's Africa Higher Education Centers of Excellence (ACEs) participated in the 10th Regional Africa Higher Education Centers of Excellence for Development Impact (ACE Impact) Country Round Table Meeting on the 17th of October 2023. Discussions centred on:
The Progress of activities at the NFU,
Project progress updates at the Country Level,
Project Restructuring and performance evaluation,
Fiduciary matters such as disbursements and procurement challenges.
And project the next steps.
Some of the issues of concern for centres in Ghana included
Delays in procurement and the need to have a permanent solution to the problem
The none performance of some critical DLIs such as institutional impact

## Slide 5: Prior to the 10th ACE Regional Workshop:
The National Facilitation Unit (NFU) carried out a number of its planned activities from its approved work. The table below presents a summary of some of the activities and their implementation status. The detailed activities are contained in the Aide Memore
ACTIVITIES | STATUS
Develop a website dedicated to ACE impact project | So far the website mockups have been completed and vetted by the IT specialist of GTEC. Their comments have since been sent back to the designers who are working on them.
Workshop for 9 ACE centers on sustainability of ACE beyond the ACE impact through industry centers collaboration | All centres received training on many concepts aimed at positioning all centers towards sustainability and industry collaboration
Develop a national qualifications framework (NFQ) to classify qualifications by level, based on learning outcomes. Training of members of the NQF Working Group is underway - August and October in Ethiopia and Kenya. The European Training Foundation (ETF) has under phase II of the African Continental Framework project provided the Commission with Three (3) Experts to guide the design, development, and implementation of the NQF – Ongoing . | The NFU is supporting a baseline analysis phase of the NQF development which has begun
Organize a country review meeting | All 9 centres, AAU, World Bank, and Ministry of Finance participated in a country review meeting on the 29th of October 2023.
General administrative support to centres Accreditaion of programmes in centres | The NFU continues to support centres in ensuring the speedy disbursement of earned DLRs. The NFU has continued to offer administrative support such as speedy accreditaion processes whiles maintaining quality.

## Slide 6: Ghana Progress Update

## Slide 7: Key Performance Indicators
Chart: Disbursements ($ million)
| Anticipated disbursement between now and June 2024 | Already disbursed | Balance
Column1 | 10.6 | 44.7554 | 4.6446
65%
Fund Utilization Rate (Sept 30 IFR)
DLI Achievement Rate
83%
75%
Current Disbursement Rate
83%
Anticipated Disbursement Rate ($4.8 million by Nov. 30)
*Includes funds for components on RSIF and national facilitation support

## Slide 8: First ACE Impact Disbursement Rates
Chart: 
| Guinea | Djibouti | Burkina Faso | Senegal | Ghana | AAU
Current Disbursement (US$ 93M) | 0.46 | 0.4 | 0.61 | 0.58 | 0.75 | 0.89
Anticipated disbursement - Nov. 30 (US$ 106.5M) | 0.62 | 0.56 | 0.72 | 0.63 | 0.83 | 0.89
Anticipated disbursement - June 2024 (US$ 124M) | 0.72 | 0.74 | 0.83 | 0.86 | 0.92 | 1
Project average - Current | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65
Project average - Nov. 30 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
Project average - June 2024 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87

## Slide 9: Fund Utilization (based on June 2023 IFRs)
Chart: Funds Spent / Funds Allocated, by country
| Ghana | Guinea | Project | Burkina Faso | Senegal | Djibouti
Series 1 | 0.65 | 0.59 | 0.55 | 0.53 | 0.34 | 0.33
Chart: Funds Spent / Funds Allocated, by center
| RWESCK | RCEES | WACCBIP | WACCI | Ghana Avg | WACWISA | CoE_Knust/ KEEP | WAGMC | ACECoR | TReCK
Series 1 | 0.86 | 0.73 | 0.7 | 0.68 | 0.65 | 0.64 | 0.63 | 0.62 | 0.61 | 0.44
Country Average Funds Utilization
Ghana ACEs Funds Utilization

## Slide 10: DLI Achievement
DLRs | DLR 3.1 (PhD Students) | DLR 3.2 (MSc Students) | DLR 3.3 (Short Course Students) | DLR 4.1 (Programme Accreditation) | DLR 4.2 (Publications) | DLR 4.3 (Teachning & Research Environment) | DLR 5.1 (Revenue) | DLR 5.2 (Internships) | DLR 5.3 (Entrepreneurship) | DLR 6.1 (Timely fiduciary reporting) | DLR 6.2 (Functioning Audit Committee & Unit) | DLR 6.3 (Web transparency) | DLR 7.1 (University-wide Regional Strategy) | DLR 7.2 (Cometitive Selection) | DLR 7.3 (Institutional Accreditation) | DLR 7.4 (PASET Regional Benchmarking) | DLR 7.5 (Institutional Impact) | Total % (All DLRs including)
WAGMC | 24% | 46% | 1% | 100% | 100% | 50% | 100% | 0% | 0% | 51% | 15% | 75% | 0% | 100% | 0% | 50% | 0% | 69%
TRECK | 98% | 100% | 88% | 0% | 100% | 50% | 100% | 94% | 0% | 55% | 30% | 99% | 100% | 100% |  | 50% | 100% | 79%
ACECOR | 95% | 81% | 100% | 100% | 95% | 50% | 100% | 44% | 0% | 55% | 23% | 88% | 100% | 100% | 0% | 50% | 0% | 80%
WACWISA | 96% | 79% | 100% | 100% | 100% | 50% | 100% | 41% | 0% | 48% | 7% | 84% | 100% | 100% | 0% | 50% | 0% | 80%
WACCI | 100% | 100% | 100% | 0% | 100% | 50% | 100% | 100% | 0% | 70% | 32% | 100% |  |  |  |  | 0% | 81%
WACCBIP | 100% | 45% | 100% | 100% | 100% | 100% | 100% | 20% | 0% | 74% | 39% | 100% |  |  |  |  | 0% | 85%
RCEES | 100% | 100% | 84% | 100% | 100% | 50% | 100% | 57% | 0% | 66% | 16% | 100% | 100% | 100% | 100% | 50% | 100% | 88%
RWESK | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 76% | 0% | 58% | 32% | 100% |  |  | 100% |  | 0% | 89%
CoE_KEEP | 100% | 100% |  | 100% |  | 100% | 100% | 48% |  | 58% | 24% | 100% |  |  |  |  |  | 95%
Total % | 90% | 84% | 84% | 78% | 99% | 67% | 100% | 53% | 0% | 59% | 24% | 94% | 80% | 100% | 40% | 50% | 25% | 83%

## Slide 11: Challenges and Key Issues
Slow Procurement processes
Challenges
Slow progress in DLI 5.3 (Entrepreneurship), DLI 6.2 (Functioning Audit Committee Units) in all centers
Apart from TRECK and RCEES, no centre has achieved any results in DLI 7.5 (Institutional Impact)
Again, RCEES and RWESCK are the only centers that have maxed out DLI 7.3 (Institutional Accreditation)
KEY ISSUES
The NFU is currently running on a tight budget line in carrying out some of its activities due to the No-Coast extension of the project. Supplementary budget support from the Bank (the restructuring process) could assist in the implementation of key activities within the action plan of the NFU.

## Slide 12: NEXT STEPS
Key Actions | Responsible | Timeline/Deadline
Organize capacity building workshop for centers | NFU | July 2024
Participate in Regional ACE Impact mid-year and PSC workshops | NFU/AAU | May 2024
Conduct a country performance review meetings (To be held before project review workshops) | NFU/Centers | March 2024
Complete and manage ACE Website. NFU will also reach out to all centers during events and outreach programs for content for the website. | NFU/Centers | January – December 2024
Complete the development of a national qualifications framework (NFQ) to classify qualifications by level, based on learning outcomes. | NFU/GTEC | June, 2024
NFU to continue to support GTEC on the development of an institutional Performance Assessment tool (Ranking mechanism) for all TEIs and their programmes in Ghana. So far, a concept not has been completed with regards to how the entire activity will be carried out. Tools for the assessment are to be developed and piloted in some selected TEIs. Once piloting is completed and modalities approved by GTEC board a road map will be developed on how the assessment will be carried out. | NFU/GTEC | January - December 2024
Conduct monitoring and evaluation of all centers to track progress and accelerate implementation | NFU/AAU | April 2024
Supervision Mission to the ACEs with Subject matter experts | NFU/AAU/Centers | January – December 2024
Participation in events organized by 9 ACEs | NFU/Centers | January – December 2024
Conduct a country performance review meeting of 2023 plan | NFU | January - 2024